## Week 8
2.5.1 | When Assigned | What Needs to be Done | Completion Criteria | When Due | Status | Hours
Tristan Dubois | 2015-08-09 | Refactor GeofenceCheck Class | -I needed to make some of the methods in GeofenceCheck type safe. -Change my Tests to reflect those changes -Change PatientServices slightly -Change a redundant method | 13/09/15 | Completed | 10/09/15 - 2.5h 12/09/15 - 1h
Hiroki | 2015-08-09 | Refactoring code for NotificationMessage | Commenting on each method of NotificationMessage Review and modify the test unit of NotificationMessage | 13/09/15 | Completed | 11/9/15 - 2h
Shirin | 2015-08-09 | Refactoring code for SaveSyncTokenTest | modify the test unit | 13/09/15 | need to fix errors
Freeman | 2015-08-09 | Code review | Code review geofencecheck | 13/9/15 | completed | 13/09/15 - 1h
Brian | 2015-08-09 | UI and Database layer | Add/Edit/Remove geo fences in MapActivity | 15/09/15 | Finished (15/09/2015) | 08/09/15 - 4h 09/09/15 - 8h 10/09/15 - 2h 12/09/15 - 8h 14/09/15 - 6h 15/09/15 - 1h
pukar | 2015-08-09 | reasearch on geofencing | research for the implenetation of geofencing | 13/09/15 | Completed | 3 hours

## Week 9
Who | When Assigned | What Needs to be Done | Completion Criteria | When Due | Status | Hours | Notes
Hiroki | T32 (Turn off notification system) | Functionalities to turn off push notification system | The user can unsubscribe a channel of push notification (For example, this will be done by creating a method by which the user can unsbscribe a channel which has been subscribed before) | 19/9/15 | 16/9... Two methods are added (setChannel, unsubsciribeChannel) to NotificationMessage class, and TestNotificationMessage class was modified so that those new methods can be tested. However, it is still needed to test those methods after integration 17/9... It was found that the unsubscribing method sometimes didn't work as expected. The method doesn't produce any exception, but apparently the subscribed channel still remains after the unsbscribing method is run, (even though there is no exception). | 3hours (16/9/15) 4hours (17/9/15)
Tristan | 15/09/15 | Check if bluetooth is a good option to check if the caretaker is near the patient | Research bluetooth | 17/09/15 | Completed - Does not seem like a good idea. Suggested to use the same mechanism as the geofence checks, but this involves having to keep track of the caretaker's location as well | 17/09/15 - 2h
Tristan | 17/09/15 | Stop geofence checks based on a value in the database. | -Get the disableGeofenceChecks of a Person. -Status set to INSIDE_FENCE -Toggle geofence checks based on the flag (disabelGeofenceChecks). -Write some tests | 20/09/15 | Completed - needs integration | 19/09/15 - 1h
Tristan | 19/09/15 | Change comments to adhere to new commenting style | -GeofenceCheck + test class -MapActivity + test class -NFC + test class -Data layer classes -Save Sync Token |  | Still need to re-comment some of the datalayers (I will do so when it is not being used by anybody else) | 19/09/15 - 1h 20/09/15 - 2h
Tristan | 17/09/15 | Documentation for the progress report | Work on the presentation | 22/09/15 |  | 2h | Don't add to the iteration plan
Shirin | 17/09/15 | add disableGoefenceChecks column to person datalayer | -column created -set defualt as false | 22/09/15 | complete | 19/09/2015 - 2h 20/09/2015- 4h
Pukar | 17/09/15 | Documentation for the progress report | work on the presentation for week 10 | 21/09/15 | completed | 4 h
Freeman | 15/9/2015 | Fix PatientFence to handle edit | PatientFence data accessor can now handle editing | 17/9/2015 | Completed | 15/9/15 - 1h
Brian | 17/09/2015 | Person Database layer | Perform UI and functions for LeaveGeoFenceButton in cataker app | 20/09/2015 | Finished UI. Waiting for database layer to connect. | 18/09/15 - 1h | Finished but Break it down.
Freeman | 20/9/2015 | Code review and merge branches | Everything is working after merge | 20/9/2015 | Merged all branches for the week | 20/9/2015 - 1.5h
Freeman | 20/9/2015 | Alert box notifications | Notification on caretaker side should appear in alert boxes | 20/9/2015 | Completed | 20/9/2015 - 2h
Freeman | 20/9/2015 | More code review and integration for add/edit/delete fences | More code review and integration for add/edit/delete fences | 20/9/2015 | Completed | 20/9/2015 - 3h
Freeman | 21/9/2015 | Polish ui and code review and bug fixing | App works without obvious force closing | 21/9/2015 | Completed | 21/9/2015 - 3h

## Week 10
Who | When Assigned | What Needs to be Done | Completion Criteria | When Due | Status | Hours
Freeman | 22/9/2015 | Update data layer for new changes, some refactoring | update data layer with tests | 30/9/2015 | Completed | 4h
Hiroki | 20/9/2015 | Add functionalities which will check the timer of geo-fences against the patient system time | Access the data base and return the time values from both the patient and the fence objects so that those time values can be compared | 27/9/2015 | Cancelled(The story was revised, and as a result this function will not be used) | 7h
Tristan Dubois | 22/09/2015 | Change the geofence check scripts to not check geofences with expired timers. | -Check if the date for a geofence is before the current date | 2015-04-09 | Completed. | 1/10/2015 - 1h 3/10/2015 - 2.5h
Tristan Dubois | 22/09/2015 | Caretaker UI for the messenging system | -UI that allows the typing of a message and a send button. -Potentialy have a window that contains all previously sent messages. | 13/09/2015 | In Progress | 04/10/2015 - 5h
Brian | 22/09/2015 | New Geofences Database Layer | Add/Remove/Edit tunnel Geofences | 2015-06-10 | Finished. However, not yet test and connect database. Waiting database layer from Freeman. This part is much more difficult than basic part. | 30/09/2015 2h 01/10/2015 8h
Freeman | 22/9/2015 | Fix CI | Explore and find a working CI solution | 2015-06-10 | found one seems to be working, called Ship.io, waiting for it to do another build and see if it works | 3/10/2015 - 3h 4/10/2015 - 2h
Shirin | 22/09/2015 | Upgrade added fence UI to handle timers | -set timer for Geofence | 2015-06-10 | in Progress | 4/10/2015-5h 5/10/2015 - 5h
Pukar | 22/09/2015 | Don't check disabled fences on the patient device | check the calender base geofence in the patient device | 2015-06-10 | Had issue with the implentation and finally completed by Tristan | 30/10/2015 - 2hr
Pukar | 22/09/2015 | Preparing for the documention | update the progess of the project and prepare the documentation for the second release | 2015-12-10 | WIP | 5/10/2015 - 2hr

## Week 11
Who | When Assigned | What Needs to be Done | Completion Criteria | When Due | Status | Hours
Hiroki | 2015-09-30 | T36.52/Choose a premade message from the patient’s phone (UI) | Make a UI on which the patient can choose a premade message, which will be sent to the caretaker via Parse.com | 2015-10-10 | completed(more testing would be needed) | 5/10/2015 - 3h 6/10/2015 - 10h 9/10/2015- 1h 11/10/2015 - 3h
Tristan | 22/09/2015 | Messenging system - Caretaker UI | -UI that allows the typing of a message and a send button. -Using the notification system to send the message over. | 2015-11-10 | More testing required | 09/10/2015 - 3.5h 10/10/2015 - 2.5h 11/10/2015 - 2h
Freeman | 2015-07-10 | Update data layer by Brian's spec | able to get largest groupid from database, | 2015-11-10 | completed | 7/10/2015 - 1.5h
Brian | 22/09/2015 | New Geofences Database Layer | Add/Remove/Edit tunnel Geofences | 2015-11-10 | completed | 06/10/2015 4h 07/10/2015 4h 09/10/2015 6h 10/10/2015 8h 11/10/2015 3h
Freeman | 2015-07-10 |  | code review, branch cleanup, bug fixes | 2015-11-10 | completed | 11/10/2015 - 5h
Freeman | 2015-07-10 |  | Add name mechanism | 2015-11-10 | completed | 11/10/2015 - 4h
Shirin | 22/09/2015 | Upgrade added fence UI to handle timers | -set timer for Geofence so that user can chose how many hours they gonna set the geofence -save the data into parse.com data base | 2015-11-10 | completed | 11/10/2015-4h

## Week 12
Who | When Assigned | What Needs to be Done | Completion Criteria | When Due | Status | Hours
Freeman |  | Integrate patient's message screen + fix tests |  |  |  | 13/10/2015 - 4h
Tristan |  | Refactoring the TokenSenderActivity so that it can be tested | -Can be tested -Still works |  | Done | 2.5h
Tristan |  | Messenger Activity Caretaker Tests | -Write tests for the messenger activity on the caretaker's side |  | Still have not figured out how to get the tests to work without having to refactor the majority of the caretaker's app. | 4h
Freeman |  | UI overhaul - make it more presentable | make it look pretty enough to feel sophisticated |  | Done | 17/10/2015 - 5h
Freeman |  | More UI polish | make it look pretty enough to feel sophisticated |  | Done | 18/10/2015 - 4h